## Summary
Defect Summary
Project Name: | Food Delivery System
Total Open Defects | 2
Total Closed Defects | 1
Total deffered Defects | 0
Grand Total | 3

## Version Control
Revision History
Sr. No. | Revision Number | Revision Date | Author | Summary
1 | 0.1 | 2021-01-12 | Bhakti | Intitial Draft
2 | 0.2 | 2021-01-13 | Payal | Incorporated review commnets given by peer
3 | 0.3 | 2021-01-18 | Girish | Incorporated review commnets given by Lead
4 | 1 | 2021-01-25 | Bhakti | Baselined Version

## Defect Report Template
Defect Report
Defect Id # | Component / Module Name | Test Case Id | Defect Description | Steps to Reproduce | Environment/Build/Release Details | Creation Date | Creator | Severity | Priority | Assignment Date | Assigned To/Developer | Estimated Time | Actual Time | Status | Resolution | Date of Resolution | Root Cause Description
TC01 | Login | TC01 | The user clicks on the link 'Login on the Portal'. The link is found unable to navigate the user to the web page displaying various pages available on the Food Delivery System Portal application. | 1. Open Browser 2. Enter URL for the website 3. Click on 'Login on the Portal' Website 4. Fill the Required data 5.Click on Submit Button | 12.0.1 | 2022-02-03 | Payal | Critical | High | 2022-02-01 | Kunal | 4Hrs | 6Hrs | Closed | Exception Handling | 2021-02-02 | Root Cause Description
TC02 | Signup | TC02 | The user clicks on the link 'Signup on the Portal'. The link is found unable to navigate the user to the web page displaying Signup on the Food Delivery System Portal application. | 1. Open Browser 2. Enter URL for the website 3. Click on 'Signup on the Portal' Website 4. Fill the Required data 5.Click on Submit Button | 12.0.1 | 2022-02-03 | Shamal | High | Medium | 2022-02-01 | Kunal | 4Hrs | 6Hrs | Open
TC03 | Make Payment | TC03 | The user clicks on the link 'Make Payemet on the Portal'. The link is found unable to navigate the user to the web page displaying various Make Payemet options available on the Food Delivery System Portal application. | 1. Open Browser 2. Enter URL for the website 3. Click on 'Make Payment on the Portal' Website 4. Select Payment Option 5.Click on Submit Button | 12.0.1 | 2022-02-03 | Bhakti | High | High | 2022-02-01 | Girish | 4Hrs | 6Hrs | Open